## Overview
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Project overview & progress per phase
PROJECT DETAILS
Source tenant | LLR
Target tenant | Kelso
Project lead
M365 Engineer
Migration tool
Planned cutover date
Number of users
Number of mailboxes (incl. shared)
Total data size (GB)
Project status | Not started
PROGRESS PER PHASE
Phase | Tab | Status | Start date | End date | Remarks
1. Preparation | 1. Preparation | Not started
2. Analysis & Inventory | 2. Analysis & Inventory | Not started
3. Identity & Users | 3. Identity | Not started
4. Exchange Online | 4. Exchange | Not started
5. OneDrive & SharePoint | 5. OneDrive-SharePoint | Not started
6. Teams | 6. Teams | Not started
7. Cutover & Aftercare | 7. Cutover & Aftercare | Not started

## 1. Preparation
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Phase 1 — Preparation: governance, access, licenses, DNS and workplace
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
PHASE 1 — PROJECT & GOVERNANCE
1 | Kick-off & define scope | Define project scope: which workloads of LLR migrate to Kelso (Exchange, OneDrive, SharePoint, Teams, apps). Identify stakeholders and decision makers. | Project lead |  | Not started
2 | Migration planning & timeline | Create a detailed plan with milestones, migration waves and the cutover date. Take holidays and business-critical periods into account. | Project lead |  | Not started
3 | Create communication plan | Inform end users in time: what changes, when, and what they need to do themselves (new password, re-register MFA, Outlook profile, Teams). | Project lead |  | Not started
4 | Define rollback / contingency plan | Describe a fallback scenario per workload in case the migration fails (revert MX, forwarding, restore from backup). | M365 Engineer |  | Not started
5 | Select migration tool & licenses | Select a tool and purchase licenses (e.g. BitTitan MigrationWiz, Quest On Demand, AvePoint Fly, ShareGate). Determine number of mailboxes/users for license count. | M365 Engineer |  | Not started
PHASE 2 — ACCESS & ACCOUNTS
6 | Global Admin access source tenant | Obtain/create a Global Administrator account in the LLR tenant (incl. MFA). Document a break-glass account. | M365 Engineer |  | Not started
7 | Global Admin access target tenant (Kelso) | Global Administrator account in the Kelso tenant. Verify sufficient rights for user creation, Exchange, SharePoint and Teams admin. | M365 Engineer |  | Not started
8 | Service accounts for migration tool | Create dedicated migration admin accounts in source and target (without MFA blocking the tool, or with app registration/modern auth). Remove afterwards. | M365 Engineer |  | Not started
9 | App registrations & API permissions | App registration in Entra ID for the migration tool with the correct Graph/EWS permissions; grant admin consent in both tenants. | M365 Engineer |  | Not started
PHASE 3 — LICENSES & TARGET TENANT CAPACITY
10 | Verify licenses in Kelso | Sufficient M365 licenses (Business Premium/E3/E5 etc.) available in Kelso for all LLR users to be migrated. | Project lead |  | Not started
11 | Check SharePoint storage capacity | Verify that the SharePoint storage quota in Kelso can hold the LLR data (use the inventory figures). | M365 Engineer |  | Not started
12 | Define naming convention | Define the UPN/email format in Kelso (e.g. firstname.lastname@kelso-domain) and identify conflicts with existing Kelso users. | M365 Engineer |  | Not started
PHASE 4 — DOMAIN & DNS PREPARATION
13 | Arrange DNS management access | Verify access to the DNS registrar/zone of the LLR domain. Lower the TTL of MX/Autodiscover records to 300-3600 sec before cutover. | M365 Engineer |  | Not started
14 | Prepare domain move | Plan for removing the mail domain from the LLR tenant and adding + verifying it in Kelso (prepare the verification TXT record). Note: the domain can only move once no objects use it anymore. | M365 Engineer |  | Not started
15 | External DNS dependencies | Inventory and reconfigure SPF, DKIM, DMARC, MTA-STS and any 3rd-party records (printers/scanners, applications using SMTP relay). | M365 Engineer |  | Not started
PHASE 5 — END USERS & WORKPLACE
16 | Inventory workstations | Overview of all PCs/laptops: Entra-joined or hybrid? Intune-managed? Plan for moving devices to the Kelso tenant. | Workplace admin |  | Not started
17 | Outlook/OneDrive profile plan | Create a procedure for a new Outlook profile and OneDrive re-link on every workstation after cutover (manual or scripted). | Workplace admin |  | Not started
18 | Mobile devices | Plan for re-enrolling phones/tablets (Outlook mobile, Teams, Company Portal, re-register MFA/Authenticator). | Workplace admin |  | Not started
19 | Password & MFA instructions | Instruction document for users: first sign-in to the Kelso tenant, set password, register MFA. | Service desk |  | Not started

## 2. Analysis & Inventory
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Phase 2 — Analysis & Inventory: map out the complete source tenant
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
INVENTORY — IDENTITY
1 | Export user overview | Export all users from LLR (Entra ID > Users or Graph/PowerShell: Get-MgUser). Record: UPN, display name, licenses, last sign-in, active/inactive. | M365 Engineer |  | Not started
2 | Shared mailboxes & resources | Export shared mailboxes, room/equipment mailboxes and their delegations (Full Access, Send As, Send on Behalf) (Get-Mailbox / Get-MailboxPermission). | M365 Engineer |  | Not started
3 | Distribution lists & M365 groups | Export all distribution groups, mail-enabled security groups and Microsoft 365 groups incl. members and owners. | M365 Engineer |  | Not started
4 | Guest accounts (B2B) | Inventory external guests in the tenant; decide which ones need to be re-invited in Kelso. | M365 Engineer |  | Not started
5 | Document admin roles | Who holds which admin role in the source tenant; determine which roles are needed in Kelso. | M365 Engineer |  | Not started
INVENTORY — EXCHANGE ONLINE
6 | Mailbox sizes & item counts | Export size and item count per mailbox (Get-MailboxStatistics) — determines migration duration and possible pre-staging. | M365 Engineer |  | Not started
7 | Archive mailboxes | Identify In-Place Archives (size; auto-expanding archives require extra attention/tooling). | M365 Engineer |  | Not started
8 | Mail flow rules & connectors | Document transport rules, connectors, anti-spam/anti-phish policies and email disclaimers to rebuild in Kelso. | M365 Engineer |  | Not started
9 | Forwarding & inbox rules | Inventory mailbox forwarding and critical inbox rules (they do not always migrate automatically). | M365 Engineer |  | Not started
10 | Aliases & proxy addresses | Export all SMTP aliases per mailbox so they can be recreated in Kelso. | M365 Engineer |  | Not started
11 | Litigation hold & retention | Identify mailboxes with Litigation Hold/retention policies — secure the data before migration (hold data does not migrate by itself). | M365 Engineer |  | Not started
INVENTORY — ONEDRIVE & SHAREPOINT
12 | OneDrive overview | Export OneDrive URL, size and file count per user (SharePoint admin center or PowerShell). | M365 Engineer |  | Not started
13 | Inventory SharePoint sites | All sites (team/communication), size, owners, last activity. Flag obsolete sites NOT to migrate (cleaning up = faster migration). | M365 Engineer |  | Not started
14 | Permissions & external sharing links | Document unique permissions, external sharing and anonymous links — external links break after migration. | M365 Engineer |  | Not started
15 | Identify obsolete data | Agree with LLR which data can be archived or deleted before the migration. | Project lead |  | Not started
INVENTORY — TEAMS
16 | Export teams & channels | Export all teams, channels (incl. private/shared channels!), members and owners. Private channels have their own SharePoint sites. | M365 Engineer |  | Not started
17 | Assess chat history | Decide whether 1:1/group chats must be migrated (slow and only partially possible; often only team channel messages are migrated). | Project lead |  | Not started
18 | Apps, tabs & connectors | Document installed Teams apps, tabs (Planner, OneNote, websites) and webhooks per team — these must be redone manually. | M365 Engineer |  | Not started
19 | Telephony/voice (if present) | Inventory Teams Phone numbers, call queues and auto attendants; plan number porting. | M365 Engineer |  | Not started
INVENTORY — APPLICATIONS & OTHER
20 | Enterprise apps & SSO | Applications that sign in via Entra SSO on the source tenant (SaaS apps, VPN, etc.) — must be reconnected to Kelso. | M365 Engineer |  | Not started
21 | Power Platform | Inventory Power Automate flows, Power Apps and Power BI reports/workspaces — these rarely migrate automatically. | M365 Engineer |  | Not started
22 | Intune & compliance policies | Document device configuration, compliance policies, conditional access and app protection policies to rebuild in Kelso. | M365 Engineer |  | Not started
23 | SMTP relay & multifunction devices | Printers, scanners and applications that send mail via the source tenant — reconfigure to Kelso. | Workplace admin |  | Not started
24 | Complete risk analysis | Summarize all findings on the 'Risks & Issues' tab and discuss with the customer. | Project lead |  | Not started

## User Mapping
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
User mapping source → target (fill in from the inventory export)
No | Display name | Source UPN (LLR) | Target UPN (Kelso) | Target license | Mailbox type | Mailbox size (GB) | OneDrive (GB) | Migrated? | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Exchange Inventory
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Exchange admin center — mailbox inventory for analysis (paste exports here)
No | Display name | Primary SMTP address | Mailbox type | Aliases | Mailbox size (GB) | Item count | Archive (GB) | Litigation hold | Forwarding to | Full Access delegates | Send As | Last logon | Migrate? | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150

## SharePoint Inventory
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
SharePoint admin center — site inventory for analysis (paste exports here)
No | Site name | Site URL | Type | Size (GB) | Files | Owner(s) | External sharing | Last activity | Connected to Team | Unique permissions | Migrate? | Target site in Kelso | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150

## Teams Inventory
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Teams admin center — team inventory for analysis (paste exports here)
No | Team name | Privacy | Owners | Members | Guests | Channels | Private/shared channels | SharePoint URL | Tabs & apps | Chat history in scope | Migrate? | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150

## Azure Inventory
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Azure / Entra ID — identity & platform inventory for analysis (paste exports here)
No | Category | Name | Details / configuration | Owner | Members / assigned users | Status in source | Required in Kelso? | Action | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150

## 3. Identity
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Phase 3 — Provision identity & users in the Kelso tenant
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
CREATE USERS IN KELSO
1 | Create user mapping table | Source UPN → target UPN mapping for all users ('User Mapping' tab). This is the basis for the migration tool. | M365 Engineer |  | Not started
2 | Provision users in Kelso | Create accounts in the Kelso tenant (CSV import, Graph or scripted). Temporarily use @kelso-onmicrosoft or the target domain as UPN. | M365 Engineer |  | Not started
3 | Assign licenses | Assign the correct licenses per user so the mailbox/OneDrive gets provisioned (speed up OneDrive pre-provisioning via PowerShell). | M365 Engineer |  | Not started
4 | Create groups & DLs | Rebuild distribution lists, security groups and M365 groups in Kelso with the correct members/owners. | M365 Engineer |  | Not started
5 | Create shared & resource mailboxes | Create shared mailboxes and room/equipment mailboxes with the same delegations as in the source. | M365 Engineer |  | Not started
SECURITY & POLICY
6 | Prepare MFA/Conditional Access | Review CA policies in Kelso; make sure migration service accounts are excluded during the migration. | M365 Engineer |  | Not started
7 | Password policy & SSPR | Distribute initial passwords via a secure channel; configure Self-Service Password Reset. | M365 Engineer |  | Not started
8 | Assign admin roles | Assign required admin roles in Kelso following least privilege. | M365 Engineer |  | Not started

## 4. Exchange
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Phase 4 — Exchange Online migration: pre-stage, cutover and aftercare
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
PRE-STAGE (BEFORE CUTOVER)
1 | Configure migration tool | Connect source (LLR) and target (Kelso) endpoints in the migration tool; import the mapping table; run a test batch with 2-3 mailboxes. | M365 Engineer |  | Not started
2 | Pre-stage sync mailboxes | First full sync of all mailbox data (mail, calendar, contacts, tasks) while users still work on the source. Start the largest mailboxes first. | M365 Engineer |  | Not started
3 | Migrate archives | Migrate In-Place Archives separately to archives in Kelso (check tool support). | M365 Engineer |  | Not started
4 | Run delta syncs | Daily delta syncs until cutover so the delta on cutover day is minimal. | M365 Engineer |  | Not started
5 | Review error reports | Review errors/skipped items per batch and resolve them (corrupt items, items >150MB, throttling). | M365 Engineer |  | Not started
CUTOVER DAY
6 | Freeze mail flow / final delta | Run the final delta sync. Optional: block sending on source mailboxes during the cutover window. | M365 Engineer |  | Not started
7 | Switch MX records | Switch MX, Autodiscover, SPF, DKIM and DMARC to the Kelso tenant. Prepare and enable DKIM in Kelso beforehand. | M365 Engineer |  | Not started
8 | Move domain (if applicable) | Detach the mail domain from the LLR tenant (first switch all aliases/UPNs to onmicrosoft) and add + verify it in Kelso; then switch UPNs and primary SMTP. | M365 Engineer |  | Not started
9 | Test mail flow | Test inbound/outbound mail (internal, external, to shared mailboxes, distribution lists). Check mail tips and signatures. | M365 Engineer |  | Not started
10 | Forwarding source → target (safety net) | Set up temporary forwarding on source mailboxes for mail that still arrives via the old route. | M365 Engineer |  | Not started
AFTER CUTOVER
11 | Post-cutover delta | Run a final delta to catch mail delivered to the source during cutover. | M365 Engineer |  | Not started
12 | Renew Outlook profiles | New Outlook profiles on all workstations; rebuild cache; restore signatures. | Service desk |  | Not started
13 | Reconfigure mobile mail | Reconnect Outlook mobile to the Kelso account. | Service desk |  | Not started

## 5. OneDrive-SharePoint
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Phase 5 — OneDrive & SharePoint data migration
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
ONEDRIVE
1 | OneDrive pre-provisioning | Pre-create OneDrives in Kelso (Request-SPOPersonalSite) so the migration tool can write immediately. | M365 Engineer |  | Not started
2 | OneDrive pre-stage sync | Full first sync of all OneDrive data; then delta syncs until cutover. | M365 Engineer |  | Not started
3 | Version history & metadata | Check tool settings: include versions, authors and timestamps where possible. | M365 Engineer |  | Not started
4 | Communicate shared links | Inform users that existing sharing links will break and items must be re-shared. | Service desk |  | Not started
5 | Re-link OneDrive client | After cutover, unlink OneDrive from the source and link it to the Kelso account on every workstation (avoid sync conflicts: rename the old folder). | Workplace admin |  | Not started
SHAREPOINT
6 | Create site structure in Kelso | Create target sites (or let the tool create them) following the agreed structure; set site owners. | M365 Engineer |  | Not started
7 | SharePoint pre-stage sync | Full sync of all sites to migrate incl. document libraries, lists and permissions; deltas until cutover. | M365 Engineer |  | Not started
8 | Validate permissions | Spot check per site: are the permissions correct (owners/members/visitors, unique permissions)? | M365 Engineer |  | Not started
9 | Shortcuts & synced libraries | Users with synced SharePoint libraries: remove the old sync, set up a new sync to the Kelso sites. | Workplace admin |  | Not started
10 | Final delta & verification | Final delta at cutover; compare item counts source vs. target; report discrepancies. | M365 Engineer |  | Not started

## 6. Teams
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Phase 6 — Microsoft Teams migration
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
TEAMS — STRUCTURE & DATA
1 | Create teams in Kelso | Rebuild teams + channels (incl. private/shared channels) or let the migration tool create them; link owners and members via the mapping table. | M365 Engineer |  | Not started
2 | Migrate channel files | Migrate the files of every channel (SharePoint behind the team); don't forget private channel sites. | M365 Engineer |  | Not started
3 | Migrate channel messages | Migrate channel conversations if desired (often as an HTML archive or via a tool with limitations). Manage user expectations. | M365 Engineer |  | Not started
4 | Chats (1:1/group) | If in scope: run chat migration (limited; alternative = readable archive). Document the decision. | Project lead |  | Not started
5 | Restore tabs, apps & connections | Manually restore Planner, OneNote, website tabs and app connections per team using the inventory. | M365 Engineer |  | Not started
TEAMS — AFTERCARE
6 | Reset Teams client | Sign users out/clear cache and sign in with the Kelso account; recreate calendar meetings if Teams links point to the source tenant. | Service desk |  | Not started
7 | Recurring meetings | Recurring Teams meetings contain links to the old tenant — have organizers recreate them after cutover. | Service desk |  | Not started
8 | Move telephony (if present) | Port/move numbers, rebuild call queues and auto attendants in Kelso. | M365 Engineer |  | Not started

## 7. Cutover & Aftercare
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Phase 7 — Cutover, validation, hypercare and decommission of the source tenant
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
CUTOVER CHECKLIST (GO/NO-GO)
1 | Go/No-Go decision | Walk through the checklist with the project team: pre-stage syncs ≥95% complete, no blocking errors, communication sent, support ready. | Project lead |  | Not started
2 | Send end-user communication | Final instruction email: timing, what to do Monday morning, where to get help. | Project lead |  | Not started
3 | Final delta all workloads | Final delta sync for mail, OneDrive, SharePoint and Teams. | M365 Engineer |  | Not started
4 | Execute DNS cutover | Switch MX/Autodiscover/SPF/DKIM/DMARC (see Exchange tab). | M365 Engineer |  | Not started
5 | Switch UPN & primary SMTP | Switch users in Kelso to the production domain as primary address. | M365 Engineer |  | Not started
6 | Restrict source tenant | Block sign-in on source accounts (after validation) to prevent confusion and double usage. | M365 Engineer |  | Not started
VALIDATION AFTER CUTOVER
7 | Mail flow validation | Test internal/external/inbound/outbound, shared mailboxes, DLs, signatures, calendar delegations. | M365 Engineer |  | Not started
8 | Data spot checks | Spot check per user group on mail, OneDrive, SharePoint and Teams files (counts and recent items). | M365 Engineer |  | Not started
9 | Workstations switched | All PCs: new profile, OneDrive linked, Teams signed in, printers/scan-to-mail working. | Workplace admin |  | Not started
10 | Start hypercare period | 1-2 weeks of elevated support; log issues on the 'Risks & Issues' tab. | Service desk |  | Not started
CLOSURE & DECOMMISSION
11 | Deliver migration report | Final report: migrated counts, open items, deviations, lessons learned for LLR. | Project lead |  | Not started
12 | Clean up forwarding & service accounts | Remove temporary forwarding, migration accounts and app registrations in both tenants. | M365 Engineer |  | Not started
13 | Decommission source tenant | After the agreed retention period: cancel licenses, secure a data export/backup, retire or park the tenant. | M365 Engineer |  | Not started
14 | Documentation & handover | Update the Kelso environment's admin documentation and hand it over to operations. | Project lead |  | Not started

## Risks & Issues
M365 Tenant-to-Tenant Migration ¦ LLR → Kelso
Risk and issue log — track all findings and incidents here
No | Date | Type | Description | Impact | Priority | Owner | Status | Resolution / Mitigation
1 |  | Risk | External sharing links (SharePoint/OneDrive) stop working after migration. | Users/external parties lose access to shared files. | High |  | Open | Communicate; re-share the most important shares after migration.
2 |  | Risk | Recurring Teams meeting links point to the old tenant. | Meetings not accessible after cutover. | High |  | Open | Have organizers recreate them after cutover.
3 |  | Risk | Microsoft throttling during large data migrations. | Migration takes longer than planned. | High |  | Open | Start pre-staging early; spread migration waves.
4 |  | Risk | Items >150 MB or corrupt items are skipped. | Missing files/mail items. | High |  | Open | Review error reports per batch; handle manually afterwards.
5 |  | Risk | Domain cannot move due to remaining objects. | Cutover delay. | High |  | Open | Switch all aliases/UPNs to .onmicrosoft.com beforehand and validate.