## Overview
M365 Tenant-to-Tenant Migration ¦ YES → Kelso
Project overview & progress per phase
PROJECT DETAILS
Source tenant | YES
Target tenant | Kelso
Project lead
M365 Engineer
Migration tool
Planned cutover date
Number of users
Number of mailboxes (incl. shared)
Total data size (GB)
Project status | Not started
PROGRESS PER PHASE
Phase | Tab | Status | Start date | End date | Remarks
1. Preparation | 1. Preparation | Not started
2. Analysis & Inventory | 2. Analysis & Inventory | Not started
3. Identity & Users | 3. Identity | Not started
4. Exchange Online | 4. Exchange | Not started
5. OneDrive & SharePoint | 5. OneDrive-SharePoint | Not started
6. Teams | 6. Teams | Not started
7. Cutover & Aftercare | 7. Cutover & Aftercare | Not started

## 1. Preparation
M365 Tenant-to-Tenant Migration ¦ YES → Kelso
Phase 1 — Preparation: governance, access, licenses, DNS and workplace
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
PHASE 1 — PROJECT & GOVERNANCE
1 | Kick-off & define scope | Define project scope: which workloads of YES migrate to Kelso (Exchange, OneDrive, SharePoint, Teams, apps). Identify stakeholders and decision makers. | Project lead |  | Not started
2 | Migration planning & timeline | Create a detailed plan with milestones, migration waves and the cutover date. Take holidays and business-critical periods into account. | Project lead |  | Not started
3 | Create communication plan | Inform end users in time: what changes, when, and what they need to do themselves (new password, re-register MFA, Outlook profile, Teams). | Project lead |  | Not started
4 | Define rollback / contingency plan | Describe a fallback scenario per workload in case the migration fails (revert MX, forwarding, restore from backup). | M365 Engineer |  | Not started
5 | Select migration tool & licenses | Select a tool and purchase licenses (e.g. BitTitan MigrationWiz, Quest On Demand, AvePoint Fly, ShareGate). Determine number of mailboxes/users for license count. | M365 Engineer |  | Not started
PHASE 2 — ACCESS & ACCOUNTS
6 | Global Admin access source tenant | Obtain/create a Global Administrator account in the YES tenant (incl. MFA). Document a break-glass account. | M365 Engineer |  | Not started
7 | Global Admin access target tenant (Kelso) | Global Administrator account in the Kelso tenant. Verify sufficient rights for user creation, Exchange, SharePoint and Teams admin. | M365 Engineer |  | Not started
8 | Service accounts for migration tool | Create dedicated migration admin accounts in source and target (without MFA blocking the tool, or with app registration/modern auth). Remove afterwards. | M365 Engineer |  | Not started
9 | App registrations & API permissions | App registration in Entra ID for the migration tool with the correct Graph/EWS permissions; grant admin consent in both tenants. | M365 Engineer |  | Not started
PHASE 3 — LICENSES & TARGET TENANT CAPACITY
10 | Verify licenses in Kelso | Sufficient M365 licenses (Business Premium/E3/E5 etc.) available in Kelso for all YES users to be migrated. | Project lead |  | Not started
11 | Check SharePoint storage capacity | Verify that the SharePoint storage quota in Kelso can hold the YES data (use the inventory figures). | M365 Engineer |  | Not started
12 | Define naming convention | Define the UPN/email format in Kelso (e.g. firstname.lastname@kelso-domain) and identify conflicts with existing Kelso users. | M365 Engineer |  | Not started
PHASE 4 — DOMAIN & DNS PREPARATION
13 | Arrange DNS management access | Verify access to the DNS registrar/zone of the YES domain. Lower the TTL of MX/Autodiscover records to 300-3600 sec before cutover. | M365 Engineer |  | Not started
14 | Prepare domain move | Plan for removing the mail domain from the YES tenant and adding + verifying it in Kelso (prepare the verification TXT record). Note: the domain can only move once no objects use it anymore. | M365 Engineer |  | Not started
15 | External DNS dependencies | Inventory and reconfigure SPF, DKIM, DMARC, MTA-STS and any 3rd-party records (printers/scanners, applications using SMTP relay). | M365 Engineer |  | Not started
PHASE 5 — END USERS & WORKPLACE
16 | Inventory workstations | Overview of all PCs/laptops: Entra-joined or hybrid? Intune-managed? Plan for moving devices to the Kelso tenant. | Workplace admin |  | Not started
17 | Outlook/OneDrive profile plan | Create a procedure for a new Outlook profile and OneDrive re-link on every workstation after cutover (manual or scripted). | Workplace admin |  | Not started
18 | Mobile devices | Plan for re-enrolling phones/tablets (Outlook mobile, Teams, Company Portal, re-register MFA/Authenticator). | Workplace admin |  | Not started
19 | Password & MFA instructions | Instruction document for users: first sign-in to the Kelso tenant, set password, register MFA. | Service desk |  | Not started

## 2. Analysis & Inventory
M365 Tenant-to-Tenant Migration ¦ YES → Kelso
Phase 2 — Analysis & Inventory: map out the complete source tenant
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
INVENTORY — IDENTITY
1 | Export user overview | Export all users from YES (Entra ID > Users or Graph/PowerShell: Get-MgUser). Record: UPN, display name, licenses, last sign-in, active/inactive. | M365 Engineer |  | Not started
2 | Shared mailboxes & resources | Export shared mailboxes, room/equipment mailboxes and their delegations (Full Access, Send As, Send on Behalf) (Get-Mailbox / Get-MailboxPermission). | M365 Engineer |  | Not started
3 | Distribution lists & M365 groups | Export all distribution groups, mail-enabled security groups and Microsoft 365 groups incl. members and owners. | M365 Engineer |  | Not started
4 | Guest accounts (B2B) | Inventory external guests in the tenant; decide which ones need to be re-invited in Kelso. | M365 Engineer |  | Not started
5 | Document admin roles | Who holds which admin role in the source tenant; determine which roles are needed in Kelso. | M365 Engineer |  | Not started
INVENTORY — EXCHANGE ONLINE
6 | Mailbox sizes & item counts | Export size and item count per mailbox (Get-MailboxStatistics) — determines migration duration and possible pre-staging. | M365 Engineer |  | Not started
7 | Archive mailboxes | Identify In-Place Archives (size; auto-expanding archives require extra attention/tooling). | M365 Engineer |  | Not started
8 | Mail flow rules & connectors | Document transport rules, connectors, anti-spam/anti-phish policies and email disclaimers to rebuild in Kelso. | M365 Engineer |  | Not started
9 | Forwarding & inbox rules | Inventory mailbox forwarding and critical inbox rules (they do not always migrate automatically). | M365 Engineer |  | Not started
10 | Aliases & proxy addresses | Export all SMTP aliases per mailbox so they can be recreated in Kelso. | M365 Engineer |  | Not started
11 | Litigation hold & retention | Identify mailboxes with Litigation Hold/retention policies — secure the data before migration (hold data does not migrate by itself). | M365 Engineer |  | Not started
INVENTORY — ONEDRIVE & SHAREPOINT
12 | OneDrive overview | Export OneDrive URL, size and file count per user (SharePoint admin center or PowerShell). | M365 Engineer |  | Not started
13 | Inventory SharePoint sites | All sites (team/communication), size, owners, last activity. Flag obsolete sites NOT to migrate (cleaning up = faster migration). | M365 Engineer |  | Not started
14 | Permissions & external sharing links | Document unique permissions, external sharing and anonymous links — external links break after migration. | M365 Engineer |  | Not started
15 | Identify obsolete data | Agree with YES which data can be archived or deleted before the migration. | Project lead |  | Not started
INVENTORY — TEAMS
16 | Export teams & channels | Export all teams, channels (incl. private/shared channels!), members and owners. Private channels have their own SharePoint sites. | M365 Engineer |  | Not started
17 | Assess chat history | Decide whether 1:1/group chats must be migrated (slow and only partially possible; often only team channel messages are migrated). | Project lead |  | Not started
18 | Apps, tabs & connectors | Document installed Teams apps, tabs (Planner, OneNote, websites) and webhooks per team — these must be redone manually. | M365 Engineer |  | Not started
19 | Telephony/voice (if present) | Inventory Teams Phone numbers, call queues and auto attendants; plan number porting. | M365 Engineer |  | Not started
INVENTORY — APPLICATIONS & OTHER
20 | Enterprise apps & SSO | Applications that sign in via Entra SSO on the source tenant (SaaS apps, VPN, etc.) — must be reconnected to Kelso. | M365 Engineer |  | Not started
21 | Power Platform | Inventory Power Automate flows, Power Apps and Power BI reports/workspaces — these rarely migrate automatically. | M365 Engineer |  | Not started
22 | Intune & compliance policies | Document device configuration, compliance policies, conditional access and app protection policies to rebuild in Kelso. | M365 Engineer |  | Not started
23 | SMTP relay & multifunction devices | Printers, scanners and applications that send mail via the source tenant — reconfigure to Kelso. | Workplace admin |  | Not started
24 | Complete risk analysis | Summarize all findings on the 'Risks & Issues' tab and discuss with the customer. | Project lead |  | Not started

## User Mapping
M365 Tenant-to-Tenant Migration ¦ YES → Kelso
User mapping source → target (fill in from the inventory export)
No | Display name | Source UPN (YES) | Target UPN (Kelso) | Target license | Mailbox type | Mailbox size (GB) | OneDrive (GB) | Migrated? | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## 3. Identity
M365 Tenant-to-Tenant Migration ¦ YES → Kelso
Phase 3 — Provision identity & users in the Kelso tenant
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
CREATE USERS IN KELSO
1 | Create user mapping table | Source UPN → target UPN mapping for all users ('User Mapping' tab). This is the basis for the migration tool. | M365 Engineer |  | Not started
2 | Provision users in Kelso | Create accounts in the Kelso tenant (CSV import, Graph or scripted). Temporarily use @kelso-onmicrosoft or the target domain as UPN. | M365 Engineer |  | Not started
3 | Assign licenses | Assign the correct licenses per user so the mailbox/OneDrive gets provisioned (speed up OneDrive pre-provisioning via PowerShell). | M365 Engineer |  | Not started
4 | Create groups & DLs | Rebuild distribution lists, security groups and M365 groups in Kelso with the correct members/owners. | M365 Engineer |  | Not started
5 | Create shared & resource mailboxes | Create shared mailboxes and room/equipment mailboxes with the same delegations as in the source. | M365 Engineer |  | Not started
SECURITY & POLICY
6 | Prepare MFA/Conditional Access | Review CA policies in Kelso; make sure migration service accounts are excluded during the migration. | M365 Engineer |  | Not started
7 | Password policy & SSPR | Distribute initial passwords via a secure channel; configure Self-Service Password Reset. | M365 Engineer |  | Not started
8 | Assign admin roles | Assign required admin roles in Kelso following least privilege. | M365 Engineer |  | Not started

## 4. Exchange
M365 Tenant-to-Tenant Migration ¦ YES → Kelso
Phase 4 — Exchange Online migration: pre-stage, cutover and aftercare
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
PRE-STAGE (BEFORE CUTOVER)
1 | Configure migration tool | Connect source (YES) and target (Kelso) endpoints in the migration tool; import the mapping table; run a test batch with 2-3 mailboxes. | M365 Engineer |  | Not started
2 | Pre-stage sync mailboxes | First full sync of all mailbox data (mail, calendar, contacts, tasks) while users still work on the source. Start the largest mailboxes first. | M365 Engineer |  | Not started
3 | Migrate archives | Migrate In-Place Archives separately to archives in Kelso (check tool support). | M365 Engineer |  | Not started
4 | Run delta syncs | Daily delta syncs until cutover so the delta on cutover day is minimal. | M365 Engineer |  | Not started
5 | Review error reports | Review errors/skipped items per batch and resolve them (corrupt items, items >150MB, throttling). | M365 Engineer |  | Not started
CUTOVER DAY
6 | Freeze mail flow / final delta | Run the final delta sync. Optional: block sending on source mailboxes during the cutover window. | M365 Engineer |  | Not started
7 | Switch MX records | Switch MX, Autodiscover, SPF, DKIM and DMARC to the Kelso tenant. Prepare and enable DKIM in Kelso beforehand. | M365 Engineer |  | Not started
8 | Move domain (if applicable) | Detach the mail domain from the YES tenant (first switch all aliases/UPNs to onmicrosoft) and add + verify it in Kelso; then switch UPNs and primary SMTP. | M365 Engineer |  | Not started
9 | Test mail flow | Test inbound/outbound mail (internal, external, to shared mailboxes, distribution lists). Check mail tips and signatures. | M365 Engineer |  | Not started
10 | Forwarding source → target (safety net) | Set up temporary forwarding on source mailboxes for mail that still arrives via the old route. | M365 Engineer |  | Not started
AFTER CUTOVER
11 | Post-cutover delta | Run a final delta to catch mail delivered to the source during cutover. | M365 Engineer |  | Not started
12 | Renew Outlook profiles | New Outlook profiles on all workstations; rebuild cache; restore signatures. | Service desk |  | Not started
13 | Reconfigure mobile mail | Reconnect Outlook mobile to the Kelso account. | Service desk |  | Not started

## 5. OneDrive-SharePoint
M365 Tenant-to-Tenant Migration ¦ YES → Kelso
Phase 5 — OneDrive & SharePoint data migration
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
ONEDRIVE
1 | OneDrive pre-provisioning | Pre-create OneDrives in Kelso (Request-SPOPersonalSite) so the migration tool can write immediately. | M365 Engineer |  | Not started
2 | OneDrive pre-stage sync | Full first sync of all OneDrive data; then delta syncs until cutover. | M365 Engineer |  | Not started
3 | Version history & metadata | Check tool settings: include versions, authors and timestamps where possible. | M365 Engineer |  | Not started
4 | Communicate shared links | Inform users that existing sharing links will break and items must be re-shared. | Service desk |  | Not started
5 | Re-link OneDrive client | After cutover, unlink OneDrive from the source and link it to the Kelso account on every workstation (avoid sync conflicts: rename the old folder). | Workplace admin |  | Not started
SHAREPOINT
6 | Create site structure in Kelso | Create target sites (or let the tool create them) following the agreed structure; set site owners. | M365 Engineer |  | Not started
7 | SharePoint pre-stage sync | Full sync of all sites to migrate incl. document libraries, lists and permissions; deltas until cutover. | M365 Engineer |  | Not started
8 | Validate permissions | Spot check per site: are the permissions correct (owners/members/visitors, unique permissions)? | M365 Engineer |  | Not started
9 | Shortcuts & synced libraries | Users with synced SharePoint libraries: remove the old sync, set up a new sync to the Kelso sites. | Workplace admin |  | Not started
10 | Final delta & verification | Final delta at cutover; compare item counts source vs. target; report discrepancies. | M365 Engineer |  | Not started

## 6. Teams
M365 Tenant-to-Tenant Migration ¦ YES → Kelso
Phase 6 — Microsoft Teams migration
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
TEAMS — STRUCTURE & DATA
1 | Create teams in Kelso | Rebuild teams + channels (incl. private/shared channels) or let the migration tool create them; link owners and members via the mapping table. | M365 Engineer |  | Not started
2 | Migrate channel files | Migrate the files of every channel (SharePoint behind the team); don't forget private channel sites. | M365 Engineer |  | Not started
3 | Migrate channel messages | Migrate channel conversations if desired (often as an HTML archive or via a tool with limitations). Manage user expectations. | M365 Engineer |  | Not started
4 | Chats (1:1/group) | If in scope: run chat migration (limited; alternative = readable archive). Document the decision. | Project lead |  | Not started
5 | Restore tabs, apps & connections | Manually restore Planner, OneNote, website tabs and app connections per team using the inventory. | M365 Engineer |  | Not started
TEAMS — AFTERCARE
6 | Reset Teams client | Sign users out/clear cache and sign in with the Kelso account; recreate calendar meetings if Teams links point to the source tenant. | Service desk |  | Not started
7 | Recurring meetings | Recurring Teams meetings contain links to the old tenant — have organizers recreate them after cutover. | Service desk |  | Not started
8 | Move telephony (if present) | Port/move numbers, rebuild call queues and auto attendants in Kelso. | M365 Engineer |  | Not started

## 7. Cutover & Aftercare
M365 Tenant-to-Tenant Migration ¦ YES → Kelso
Phase 7 — Cutover, validation, hypercare and decommission of the source tenant
No | Task | Description / Instructions | Owner | Priority | Status | Due date | Completed on | Notes
CUTOVER CHECKLIST (GO/NO-GO)
1 | Go/No-Go decision | Walk through the checklist with the project team: pre-stage syncs ≥95% complete, no blocking errors, communication sent, support ready. | Project lead |  | Not started
2 | Send end-user communication | Final instruction email: timing, what to do Monday morning, where to get help. | Project lead |  | Not started
3 | Final delta all workloads | Final delta sync for mail, OneDrive, SharePoint and Teams. | M365 Engineer |  | Not started
4 | Execute DNS cutover | Switch MX/Autodiscover/SPF/DKIM/DMARC (see Exchange tab). | M365 Engineer |  | Not started
5 | Switch UPN & primary SMTP | Switch users in Kelso to the production domain as primary address. | M365 Engineer |  | Not started
6 | Restrict source tenant | Block sign-in on source accounts (after validation) to prevent confusion and double usage. | M365 Engineer |  | Not started
VALIDATION AFTER CUTOVER
7 | Mail flow validation | Test internal/external/inbound/outbound, shared mailboxes, DLs, signatures, calendar delegations. | M365 Engineer |  | Not started
8 | Data spot checks | Spot check per user group on mail, OneDrive, SharePoint and Teams files (counts and recent items). | M365 Engineer |  | Not started
9 | Workstations switched | All PCs: new profile, OneDrive linked, Teams signed in, printers/scan-to-mail working. | Workplace admin |  | Not started
10 | Start hypercare period | 1-2 weeks of elevated support; log issues on the 'Risks & Issues' tab. | Service desk |  | Not started
CLOSURE & DECOMMISSION
11 | Deliver migration report | Final report: migrated counts, open items, deviations, lessons learned for YES. | Project lead |  | Not started
12 | Clean up forwarding & service accounts | Remove temporary forwarding, migration accounts and app registrations in both tenants. | M365 Engineer |  | Not started
13 | Decommission source tenant | After the agreed retention period: cancel licenses, secure a data export/backup, retire or park the tenant. | M365 Engineer |  | Not started
14 | Documentation & handover | Update the Kelso environment's admin documentation and hand it over to operations. | Project lead |  | Not started

## Risks & Issues
M365 Tenant-to-Tenant Migration ¦ YES → Kelso
Risk and issue log — track all findings and incidents here
No | Date | Type | Description | Impact | Priority | Owner | Status | Resolution / Mitigation
1 |  | Risk | External sharing links (SharePoint/OneDrive) stop working after migration. | Users/external parties lose access to shared files. | High |  | Open | Communicate; re-share the most important shares after migration.
2 |  | Risk | Recurring Teams meeting links point to the old tenant. | Meetings not accessible after cutover. | High |  | Open | Have organizers recreate them after cutover.
3 |  | Risk | Microsoft throttling during large data migrations. | Migration takes longer than planned. | High |  | Open | Start pre-staging early; spread migration waves.
4 |  | Risk | Items >150 MB or corrupt items are skipped. | Missing files/mail items. | High |  | Open | Review error reports per batch; handle manually afterwards.
5 |  | Risk | Domain cannot move due to remaining objects. | Cutover delay. | High |  | Open | Switch all aliases/UPNs to .onmicrosoft.com beforehand and validate.